## 01_실적입력
project_name | AI Construction MVP Demo Site
activity_id | work_date | planned_qty | actual_qty | workers | equipment | owner | remarks
A-100
A-200
A-210
A-300
A-400
A-500

## 02_원가입력
project_name | AI Construction MVP Demo Site
activity_id | contract_amount | execution_budget | invested_cost | billing_amount | remarks
A-100
A-200
A-210
A-300
A-400
A-500

## 03_자재검측
project_name | AI Construction MVP Demo Site
activity_id | material_name | expected_date | actual_date | inspection_type | planned_date | approval_date | status
A-100
A-200
A-210
A-300
A-400
A-500

## 04_공정표
activity_id | name | discipline | zone | start_date | finish_date | status
A-100 | Normal concrete curing | 건축 | 1F | 2026-05-11 | 2026-05-25 | completed
A-200 | Delayed rebar assembly | 토목 | B1 | 2026-05-06 | 2026-05-14 | in_progress
A-210 | Concrete pour blocked by predecessor | 토목 | B1 | 2026-05-19 | 2026-05-22 | ready
A-300 | MEP ceiling framing cost overrun | 기계설비 | 2F | 2026-05-12 | 2026-05-20 | in_progress
A-400 | Fire pump delivery delay | 소방설비 | Machine Room | 2026-05-10 | 2026-05-21 | in_progress
A-500 | Electrical panel inspection delay | 전기설비 | EPS | 2026-05-08 | 2026-05-17 | in_progress

## 05_대시보드
현장소장 대시보드
현장명 | AI Construction MVP Demo Site
전체 계획공정률
전체 실적공정률
공정 차이
원가집행률
기성률
부진공정 수

## 06_부진공정
activity_id | name | reason | owner | risk

## 07_보고서
주간 공정회의자료
section | content