## 05_대시보드
현장소장 대시보드
현장명 | AI Construction MVP Demo Site
전체 실적공정률 | 38.96
전체 계획공정률 | 62
공정 차이 | -23.04
원가집행률 | 72
기성률 | 38.46
부진공정 수 | 5
위험공종 | civil
핵심 리스크 | 원가 과투입 검토 필요

## 금주 실적
activity_id | name | discipline | zone | this_week_actual | actual_progress_pct
A-100 | Normal concrete curing | architecture | 1F | Completed curing inspection | 100
A-200 | Delayed rebar assembly | civil | B1 | Rebar assembly reached 55% | 55
A-210 | Concrete pour blocked by predecessor | civil | B1 | Waiting for predecessor completion | 0
A-300 | MEP ceiling framing cost overrun | mechanical | 2F | Framing progressed with extra labor | 45
A-400 | Fire pump delivery delay | fire_protection | Machine Room | Pump not delivered | 0
A-500 | Electrical panel inspection delay | electrical | EPS | Panel installation partially complete | 40

## 부진공정 TOP 10
activity_id | name | discipline | zone | reason_code | owner | risk_score | reason
A-200 | Delayed rebar assembly | civil | B1 | schedule_progress_delay | Lee | 33 | Delayed rebar assembly progress delay: planned 80.0%, actual 55.0%, gap 25.0%.
A-210 | Concrete pour blocked by predecessor | civil | B1 | schedule_progress_delay | Park | 38 | Concrete pour blocked by predecessor progress delay: planned 30.0%, actual 0.0%, gap 30.0%.
A-300 | MEP ceiling framing cost overrun | mechanical | 2F | schedule_progress_delay | Choi | 15 | MEP ceiling framing cost overrun progress delay: planned 60.0%, actual 45.0%, gap 15.0%.
A-400 | Fire pump delivery delay | fire_protection | Machine Room | schedule_progress_delay | Jung | 51 | Fire pump delivery delay progress delay: planned 40.0%, actual 0.0%, gap 40.0%.
A-500 | Electrical panel inspection delay | electrical | EPS | schedule_progress_delay |  | 44 | Electrical panel inspection delay progress delay: planned 70.0%, actual 40.0%, gap 30.0%.

## 만회대책 초안
activity_id | name | reason_code | candidate | review_note | narrative
A-200 | Delayed rebar assembly | schedule_progress_delay | 현장 협의 후보 | 검토 필요 | Delayed rebar assembly 지연 원인(schedule_progress_delay)에 대한 만회대책 초안입니다. 검토 필요. 1. 현장 협의 후보: 담당자, 협력사, 감리와 원인 및 만회 가능 조건을 검토하는 초안입니다. 검토 필요.
A-210 | Concrete pour blocked by predecessor | schedule_progress_delay | 현장 협의 후보 | 검토 필요 | Concrete pour blocked by predecessor 지연 원인(schedule_progress_delay)에 대한 만회대책 초안입니다. 검토 필요. 1. 현장 협의 후보: 담당자, 협력사, 감리와 원인 및 만회 가능 조건을 검토하는 초안입니다. 검토 필요.
A-300 | MEP ceiling framing cost overrun | schedule_progress_delay | 현장 협의 후보 | 검토 필요 | MEP ceiling framing cost overrun 지연 원인(schedule_progress_delay)에 대한 만회대책 초안입니다. 검토 필요. 1. 현장 협의 후보: 담당자, 협력사, 감리와 원인 및 만회 가능 조건을 검토하는 초안입니다. 검토 필요.
A-400 | Fire pump delivery delay | schedule_progress_delay | 현장 협의 후보 | 검토 필요 | Fire pump delivery delay 지연 원인(schedule_progress_delay)에 대한 만회대책 초안입니다. 검토 필요. 1. 현장 협의 후보: 담당자, 협력사, 감리와 원인 및 만회 가능 조건을 검토하는 초안입니다. 검토 필요.
A-500 | Electrical panel inspection delay | schedule_progress_delay | 현장 협의 후보 | 검토 필요 | Electrical panel inspection delay 지연 원인(schedule_progress_delay)에 대한 만회대책 초안입니다. 검토 필요. 1. 현장 협의 후보: 담당자, 협력사, 감리와 원인 및 만회 가능 조건을 검토하는 초안입니다. 검토 필요.

## 원가현황
activity_id | name | progress_pct | execution_budget | invested_cost | cost_execution_rate | billing_rate | overrun
A-300 | MEP ceiling framing cost overrun | 45 | 1000 | 720 | 72 | 38.46 | TRUE

## 다음 주 예정공정
activity_id | name | discipline | zone | next_week_plan
A-100 | Normal concrete curing | architecture | 1F | Release support material
A-200 | Delayed rebar assembly | civil | B1 | Add crew and close remaining section
A-210 | Concrete pour blocked by predecessor | civil | B1 | Start pour after rebar inspection
A-300 | MEP ceiling framing cost overrun | mechanical | 2F | Review crew productivity
A-400 | Fire pump delivery delay | fire_protection | Machine Room | Confirm delivery and prepare base
A-500 | Electrical panel inspection delay | electrical | EPS | Complete inspection and energization prep

## 간트 데이터
activity_id | name | start_date | finish_date | status | actual_progress_pct
A-100 | Normal concrete curing | 2026-05-11 | 2026-05-25 | completed | 100
A-200 | Delayed rebar assembly | 2026-05-06 | 2026-05-14 | in_progress | 55
A-210 | Concrete pour blocked by predecessor | 2026-05-19 | 2026-05-22 | ready | 0
A-300 | MEP ceiling framing cost overrun | 2026-05-12 | 2026-05-20 | in_progress | 45
A-400 | Fire pump delivery delay | 2026-05-10 | 2026-05-21 | in_progress | 0
A-500 | Electrical panel inspection delay | 2026-05-08 | 2026-05-17 | in_progress | 40

## 07_보고서
주간 공정회의자료
section | content
report_style | weekly_meeting
delayed_activity_count | 5
recovery_draft_count | 5
language_policy | 만회대책은 초안/후보이며 현장 검토 필요